ITU Capital Projects Master Project List and Activities 	           		              11/02/2012

(Priority Action in Red) ( = New Information)

Campus Drive West Campus Connector Road	Brad Glatfelter___________________________________

- Completion November 2013. Scope includes construction of restrooms, maintenance building, tennis courts, pavilion and various athletic fields.

- More segment design meetings in following weeks.

- Plans on Facilities Docushare.

- Site work likely to begin in the 4th quarter.

Exploratory Hall (S&T II) Addition/Renovation	  Alex Iszard				           Tuesdays 9:00

- Substantial completion 3-23-2013. Classroom use in fall 2013. S&T II is now Exploratory Hall.

- From Facilities “Project Partners” meeting, planned move is week of May 20, 2013. Telecom rooms scheduled complete on Jan 15, 2013.

- Walk through to check jack locations underway.

- Temporary network switches for BAS monitoring installed.

- WAP plan being developed.

- Site requires Safety Orientation, helmet, vest, glasses, and hard shoes; access via trailer check in only.

- Fenwick Library Expansion               		Brian Snyder

- Occupancy August 2014.

- General Contractor OSP work started.

- Drawing files posted, review comments needed in mid November.

- Net Eng to provide outage plan for user distribution.

- Weekly teleconference design meetings underway.

Fine Arts Renovation 				Hieu Tran 			         Alt. Wednesdays 10:00

- Substantial completion is May 10, 2013. Construction schedules posted on Docushare.

- Contractor is proposing product alternate, waiting for submittal to respond to. First cabling submittal rejected. Meeting cancelled, reschedule TBD.

- Request into eVA for cable for JC loading dock security camera.

- Will conduct a pre-construction meeting prior to cable work starting.

- Site requirements: check in with Mason Inspector and wearing hardhat, neon vest, glasses and boots.

Housing VIIIB	 Shenandoah				Nancy Pickens

- Construction start 01/13. 300 Freshman beds near Presidents Park. Completion expected Summer ’14.

- Facilities reviewing RFPs.

- PWC PPEA Life Sciences Building 		Micky Boeckl		                     Alt. Wednesdays 10:00

- January 2013 completion. 75,000 square feet, 3 stories, BSL II.

- All floors and roof slab poured.

- IT Wiring pricing in for review.

- 60% drawings on Docushare, they are responsive to our comments, details should be reviewed.

- OSP conduit installed.

- PWC PPEA Graduate Dorm	- Beacon Hall		Micky Boeckl		                     Alt. Wednesdays 10:00

- Additional WAPs cost approval received from PM. Installation underway.

- Cooling unit in MDF being repaired by contractor.

- BCOM approval for occupancy granted 10/24.

- Students move in Nov 1. Manager occupying his apartment last weekend.

- Punchlist done and sent to project.

- Phones and office pc installed. All student room dialtone ready.

- Awaiting as builts and test results.

- Upper level student housing – 152 beds, 4 stories, above a floor of 10,000 GSF Mason space and 15,000 GSF retail space with 212 parking spaces.

- Point of View Center 				Nancy Pickens___________________________________

- Startup delayed by environmental approval requirements.

- Network site provider connection proposal and costs needed.

- University Commons Renovation                	Hieu Tran				         Tuesdays 11:00

- Outdoor WAP conduit and box in place awaiting device installation.

- BCOM had 4 items for correction before Certificate of Occupancy.

- Apartment still to be occupied next week. Dialtone installed.

- Office furniture delivered Nov 1.

Farther Out and Smaller Projects

Potomac Science Center Belmont Bay		Alex Iszard

- Preliminary design meetings underway, fiber service to site is a challenge.

- Location near Belmont Bay Marina.

Shenandoah Dining Expansion			Hieu Tran

- Schematic closer to approval and completion. $8 million project. Construction likely concurrent with Housing VIIIB.

- RFPs under review.

- Possible Fall 2014 completion.

Housing VIIIB	 Rappahannock			Nancy Pickens

- Completion planned Fall 2015. Located north of Fenwick, partially on Lecture Hall site.

- RFP input due end of October.

- Currently 210 beds, 13 classrooms. Mixed use of housing, classroom and academic center.

- Ductbank relocation part of the plan.