## Intro
Weekly Project Tracking Spreadsheets
by David Teten
www.Teten.com
www.TheVirtualHandshake.com
This file contains two sample project tracking sheets, one for individual contributors
and one for group managers
How to use this spreadsheet (for team members):
1 | Save with a file name in this format: Smith John 20080618 (for week ending June 18th, 2008).
2 | Fill out with all of your responsibilities, both long term projects and short term tasks.
3 | Update the file during the week.
4 | When you complete a task, just move it below the green line.
5 | Each Friday, send it back to your manager..
6 | On Monday, save a new version of the file with the following Friday's end date.
7 | Erase all completed tasks from the prior week.
8 | Rinse and repeat.
This spreadsheet is licensed under the
Creative Commons Attribution License
You may use any content from this file however you want, so long
as you credit David Teten.
and provide a link back to the page on which the content is located.

## Timesheet-Single Contributor
Weekly Project Tracking
Name: |  | ________________________________ | Title: | ___________________ |  | Week End: | ________________________________
Priority (1- 4) | Task |  | Hours | Time to Complete | Deadline | Risk Factors | Requiring Mgr Attention | Orginal Est. (Hrs) | Hrs Used To Date | Est. Total Needed to Complete | % Overrun (Underrun)
Tasks in Progress
|  |  | 10 | 30 |  |  |  | 160 | 130 | 160 | 0%
Completed Tasks
Total |  |  | 10 | 30 |  |  |  | 160 | 130 | 160 | 0%
Plans for Next Week
Comments

## Projects-Group Manager
Weekly Project Tracking
Name: |  | ________________________________ | Title: | ___________________ |  | Week End: | ________________________________ | ________________________________
Priority (1- 4) | Task |  | Owner | Support | Deadline | Status | Risk Factors | Requiring Mgr Attention
Tasks in Progress
|  |  | David | Scott
Completed Tasks
Total |  |  | 0 | 0
Plans for Next Week
Comments