## 9 Month Plan
Host
Client
Event Date/Time
Event Coordinator
Location
Event Date | 2006-02-24
9 Month Plan | Task | Actual Date Completed | Comments
2005-05-30 | Define Purpose of event and target audience
2005-05-30 | Decide on Event format
2005-05-30 | Conduct Site Visits
2005-06-29 | Create and Maintain Event Budget
2005-06-29 | Confirm Date and Venue
2005-06-29 | Secure speakers, entertainment
2005-07-29 | Determine Method of communicating event (e-mail, direct mail, advertisment)
2005-07-29 | Begin to gather data necessary for invitations
2005-07-29 | Request Catering Proposals
2005-08-28 | Begin creating event materials
2005-08-28 | Select Caterer
2005-08-28 | Determine other necessary rentals (AV, tables, chairs, linens, china)
2005-09-27 | Finalize Guest List
2005-09-27 | Request Rental Quotes
2005-09-27 | Finalize text and design for event materials
2005-10-27 | Mail Save the Date Cards
2005-11-26 | Revisit venue to determine preferred room layout, traffic flow, and color themes
2005-11-26 | Request food tasting
2005-11-26 | Update mailing list from any returns on Save the Date mailing
2005-11-26 | Hire a florist
2005-11-26 | Final approval of invitation
2005-11-26 | Arrange Parking-Contact Access Services or Hire Valet
2005-12-26 | Send Invitations
2005-12-26 | Create and Maintain RSVP Report
2005-12-26 | Finalize menu and all rental contracts
2005-12-26 | Select/Order Event Giveaways
2006-01-25 | Organize invitaiton responses
2006-01-25 | Once RSVP deadline has passed, make follow-up calls to those who have not responded and courtesy reminder calls to those that will be attending
2006-01-25 | Request Security
2006-01-25 | Request Custodial/Grounds
2006-01-25 | Contact Campus Movers
2006-02-03 | Finalize and Print Programs
2006-02-10 | Create Campus Event Briefing
DAY OF EVENT | Thorough review of event checklist
POST EVENT | Send out personal thank you's
POST EVENT | Solicit feedback from attendees and also from those who weren't able to attend
POST EVENT | Satisfy all contracts and agreements
POST EVENT | Make a list indicating possible areas of improvement
POST EVENT | Make notes about vendors that you might want to remember next time

## 6 Month Plan
Host
Client
Event Date/Time
Event Coordinator
Location
Event Date | 2006-02-24
6 Month Plan | Task | Actual Date Completed | Comments
2005-08-28 | Define Purpose of event and target audience
2005-08-28 | Decide on Event format
2005-08-28 | Conduct Site Visits
2005-09-27 | Create and Maintain Event Budget
2005-09-27 | Confirm Date and Venue
2005-09-27 | Secure speakers, entertainment
2005-09-27 | Determine Method of communicating event (e-mail, direct mail, advertisment)
2005-09-27 | Begin to gather data necessary for invitations
2005-09-27 | Request Catering Proposals
2005-10-27 | Begin creating event materials
2005-10-27 | Select Caterer
2005-11-26 | Determine other necessary rentals (AV, tables, chairs, linens, china)
2005-11-26 | Finalize Guest List
2005-11-26 | Request Rental Quotes
2005-11-26 | Finalize text and design for event materials
2005-11-26 | Mail Save the Date Cards
2005-11-26 | Revisit venue to determine preferred room layout, traffic flow, and color themes
2005-12-26 | Request food tasting
2005-12-26 | Update mailing list from any returns on Save the Date mailing
2005-12-26 | Hire a florist
2005-12-26 | Final approval of invitation
2005-12-26 | Arrange Parking-Contact Access Services or Hire Valet
2006-01-13 | Send Invitations
2006-01-13 | Create and Maintain RSVP Report
2006-01-25 | Finalize menu and all rental contracts
2006-01-25 | Select/Order Event Giveaways
2006-01-25 | Organize invitaiton responses
2006-01-25 | Once RSVP deadline has passed, make follow-up calls to those who have not responded and courtesy reminder calls to those that will be attending
2006-01-25 | Request Security
2006-01-25 | Request Custodial/Grounds
2006-01-25 | Contact Campus Movers
2006-02-03 | Finalize and Print Programs
2006-02-10 | Create Campus Event Briefing
DAY OF EVENT | Thorough review of event checklist
POST EVENT | Send out personal thank you's
POST EVENT | Solicit feedback from attendees and also from those who weren't able to attend
POST EVENT | Satisfy all contracts and agreements
POST EVENT | Make a list indicating possible areas of improvement
POST EVENT | Make notes about vendors that you might want to remember next time

## 3 Month Plan
Host
Client
Event Date/Time
Event Coordinator
Location
Event Date | 2006-02-24
3 Month Plan | Task | Actual Date Completed | Comments
2005-11-26 | Define Purpose of event and target audience
2005-11-26 | Decide on Event format
2005-11-26 | Conduct Site Visits
2005-11-26 | Create and Maintain Event Budget
2005-11-26 | Confirm Date and Venue
2005-11-26 | Secure speakers, entertainment
2005-11-26 | Determine Method of communicating event (e-mail, direct mail, advertisment)
2005-11-26 | Begin to gather data necessary for invitations
2005-11-26 | Request Catering Proposals
2005-12-06 | Begin creating event materials
2005-12-06 | Select Caterer
2005-12-11 | Determine other necessary rentals (AV, tables, chairs, linens, china)
2005-12-11 | Finalize Guest List
2005-12-21 | Request Rental Quotes
2005-12-21 | Finalize text and design for event materials
2005-12-01 | Mail Save the Date Cards
2005-12-11 | Revisit venue to determine preferred room layout, traffic flow, and color themes
2005-12-16 | Request food tasting
2005-12-16 | Update mailing list from any returns on Save the Date mailing
2005-12-11 | Hire a florist
2005-12-16 | Final approval of invitation
2005-12-11 | Arrange Parking-Contact Access Services or Hire Valet
2006-01-13 | Send Invitations
2006-01-13 | Create and Maintain RSVP Report
2006-01-25 | Finalize menu and all rental contracts
2006-01-25 | Select/Order Event Giveaways
2006-01-25 | Organize invitaiton responses
2006-01-25 | Once RSVP deadline has passed, make follow-up calls to those who have not responded and courtesy reminder calls to those that will be attending
2006-01-25 | Request Security
2006-01-25 | Request Custodial/Grounds
2006-01-25 | Contact Campus Movers
2006-02-03 | Finalize and Print Programs
2006-02-10 | Create Campus Event Briefing
DAY OF EVENT | Thorough review of event checklist
POST EVENT | Send out personal thank you's
POST EVENT | Solicit feedback from attendees and also from those who weren't able to attend
POST EVENT | Satisfy all contracts and agreements
POST EVENT | Make a list indicating possible areas of improvement
POST EVENT | Make notes about vendors that you might want to remember next time

## 1 Month Plan
Host
Client
Event Date/Time
Event Coordinator
Location
Event Date | 2008-04-11
1 Month Plan | Task | Date Completed | Comments
2008-03-12 | Define Purpose of event and target audience
2008-03-12 | Decide on Event format
2008-03-12 | Conduct Site Visits
2008-03-12 | Create and Maintain Event Budget
2008-03-12 | Confirm Date and Venue
2008-03-12 | Secure speakers, entertainment
2008-03-12 | Determine Method of communicating event (e-mail, direct mail, advertisment)
2008-03-14 | Begin to gather data necessary for invitations
2008-03-14 | Request Catering Proposals
2008-03-14 | Begin creating event materials
2008-03-17 | Select Caterer
2008-03-17 | Determine other necessary rentals (AV, tables, chairs, linens, china)
2008-03-17 | Finalize Guest List
2008-03-18 | Request Rental Quotes
2008-03-18 | Finalize text and design for event materials
NA | Mail Save the Date Cards
2008-03-21 | Revisit venue to determine preferred room layout, traffic flow, and color themes
2008-03-21 | Request food tasting
NA | Update mailing list from any returns on Save the Date mailing
2008-03-21 | Select décor
2008-03-21 | Final approval of invitation
2008-03-21 | Arrange Parking-Contact Access Services or Hire Valet
2008-03-14 | Send Invitations
2008-03-14 | Create and Maintain RSVP Report
2008-03-21 | Finalize menu and all rental contracts
2008-03-14 | Select/Order Event Giveaways
2008-03-14 | Organize invitaiton responses
2008-03-28 | Once RSVP deadline has passed, make follow-up calls to those who have not responded and courtesy reminder calls to those that will be attending
2008-03-14 | Request Security
2008-03-14 | Request Custodial/Grounds
2008-03-14 | Contact Campus Movers
2008-03-21 | Finalize and Print Programs
2008-03-28 | Create Campus Event Briefing
DAY OF EVENT | Thorough review of event checklist
POST EVENT | Send out personal thank you's
POST EVENT | Solicit feedback from attendees and also from those who weren't able to attend
POST EVENT | Satisfy all contracts and agreements
POST EVENT | Make a list indicating possible areas of improvement you want to remember next time