## Instructions
Column | Instructions For Completing This Document
Complete the Project Name, NC, Project Manager Name, and Project Description fields
For each change request identified, complete the following:
A | ID: A unique ID number used to identify the change request in the change management tracking log.
B | Current Status: This column should be populated with the change request's current status. o Open: The change request is currently open but has not yet been addressed. o Work In Progress: The change request is being actively worked to develop a resolution. o Closed: The change request is no longer considered an active project threat and can be closed with or without resolution. Some other potential options include: o Late: The change request resolution is not yet resolved and it is past the expected resolution date. o On Hold: The change request has been put on hold. o Combined: Two change requests found to be similar have been combined.
C | Priority: This column should be populated with the priority of the change request. Valid options include the following: High, Medium, Low. These are defined as follows: o Critical: change request will stop project progress if not resolved. o High: change request will likely move the project back in terms of budget or timeline, or will materially affect quality or scope. o Medium: change request will have material effect on project, has potential to be moved to high category and/or requires significant resources to manage. o Low: change request is expected to have a moderate effect on the project, but will require resources to address.
D | Change Request Description: This column should be populated with a description of the change request.
E | Assigned to Owner: This column should be populated with the name of the change requests owner. The individual most responsible for working towards resolving the change request.
F | Expected Resolution Date: This column should be populated with the date that the change request is expected to be resolved.
G | Escalation Required (Y/N): This column should be populated with “Yes” if the change request needs to be escalated and “No” if escalation is not needed to resolve the change request.
H | Action Steps: This column should be populated with the proposed steps to address the change request. Examples include, but are not limited to, developing alternatives analysis or submitting a change request.
I | Impact Summary: This column should be populated with a description of the impact of the change request. The impact may be expressed in terms of one or more of the following: schedule, scope, resources, and space. The impact description should also include a reference to any milestones impacted.
J | Change Request Type: This column should be populated with the change request type. Valid options include the following: Product, Project, Other. These are defined as follows: o Product: The change request impacts the products being developed. o Project: The change request impacts the project developing the product. o Other: The change request impacts other areas.
K | Date Identified: This column should be populated with the date that the change request was identified.
L | Associated ID(s): This column should contain the project ID of any associated milestones that may be impacted by a change request or that the change request is dependent upon for resolution. Please note, this value may require coordination with other program/project managers.
M | Entered By: This column should be populated with the name of the individual who first identified the change request.
N | Actual Resolution Date: This column should be populated with the date that the change request was actually resolved.
O | Final Resolution & Rationale: This column should be populated with a description of the final resolution of and rationale for the change request. The resolution may be expressed in terms of one or more of the following: schedule, scope, resources, and space. The resolution description should also include a reference to the milestones impacted.
Column | Instructions for Changing the Contents of Drop-Down Menus
B, C G, J | Highlight the cell where you wish to change the content of the drop down menu. From the file menu click "Data" -> "Validation" and change the content of the source field.
Column | Instructions For Filtering Data
Any | Highlight the header of the cell you wish to filter data on. From the file menu click "Date" -> "Filter" ->"Auto Filter". Then select your filter criteria from the drop down menu that appears on your header cell.

## Change_Management_Log
CHANGE MANAGEMENT LOG | [7 empty] | CHANGE MANAGEMENT LOG
Project Name: |  |  | <optional> |  |  |  |  | Project Name: | <optional>
National Center: |  |  | <required> |  |  |  |  | National Center: | <required>
Project Manager Name: |  |  | <required> |  |  |  |  | Project Manager Name: | <required>
Project Description: |  |  | <required> |  |  |  |  | Project Description: | <required>
ID | Current Status | Priority | Change Request Description | Assigned To Owner | Expected Resolution Date | Escalation Required (Y/N)? | Action Steps | Impact Summary | Change Request Type | Date Identified | Assoc ID | Entered By | Actual Resolution Date | Final Resolution & Rationale
| Open | Critical | EXAMPLE: Request for product functionality increase |  |  | Yes | EXAMPLE: Analyze impact of requested change and then meet with the change control board (CCB) to present findings for final decision on the requested change | EXAMPLE: Project scope, schedule, resources, and potentially budget may all be impacted | Product | 2006-01-01 |  |  |  | EXAMPLE: The CCB has approved the change
| Work In Progress | High | EXAMPLE: The schedule slipped due to unexpected weather related events |  |  | No | EXAMPLE: Adjust the schedule to account for the weather related events | EXAMPLE: Project schedules, resources, and possibly budget may all be impacted | Project | 2006-01-01 |  |  |  | EXAMPLE: Updated schedule reviewed and approved
| Closed | Medium | [6 empty] | Other
Low
Note on A6: • ID: A unique ID number used to identify the change request in the change management log.
Note on L6: • Associated Milestone ID(s): This column should contain the project ID of any associated milestones that may be impacted by a change request or that the change request is dependent upon for resolution. Please note, this value may require coordination with other program/project managers.
Note on C6: • Priority: This column should be populated with the priority of the change request. Valid options include the following: High, Medium, Low. These are defined as follows: o Critical: Change Request will stop project progress if not resolved. o High: Change Request will likely move the project back in terms of budget or timeline, or will materially affect quality or scope. o Medium: Change Request will have material effect on project, has potential to be moved to high category and/or requires significant resources to manage. o Low: Change Request is expected to have a moderate effect on the project, but will require resources to address.
Note on D6: • Change Request Description: This column should be populated with a description of the change request.
Note on I6: • Impact Summary: This column should be populated with a description of the impact of the change request. The impact may be expressed in terms of one or more of the following: schedule, scope, resources, and space. The impact description should also include a reference to any milestones impacted.
Note on H6: • Action Steps: This column should be populated with the proposed steps to address the change request. Examples include, but are not limited to, developing alternatives analysis or submitting a change request.
Note on J6: • Change Request Type: This column should be populated with the change request type. Valid options include the following: Product, Project, Other. These are defined as follows: o Product: The change request impacts the products being developed. o Project: The change request impacts the project developing the product. o Other: The change request impacts other areas.
Note on B6: • Current Status: This column should be populated with the change request's current status. o Open: The change request is currently open but has not yet been addressed. o Work In Progress: The change request is being actively worked to develop a resolution. o Closed: The change request is no longer considered an active project threat and can be closed with or without resolution. Some other potential options include: o Late: The change request resolution is not yet resolved and it is past the expected resolution date. o On Hold: The change request has been put on hold. o Combined: Two change request found to be similar have been combined.
Note on K6: • Date Identified: This column should be populated with the date that the change request was identified.
Note on M6: • Entered By: This column should be populated with the name of the individual who first identified the change request.
Note on E6: • Assigned To Owner: This column should be populated by the name of the change request owner. The individual most responsible for working towards resolving the change request.
Note on G6: • Escalation Required (Y/N): This column should be populated with “Yes” if the change request needs to be escalated and “No” if escalation is not needed to resolve the change request.
Note on F6: • Expected Resolution Date: This column should be populated with the date that the change request is expected to be resolved.
Note on N6: • Actual Resolution Date: This column should be populated with the date that the change request was actually resolved.
Note on O6: • Final Resolution & Rationale: This column should be populated with a description of the final resolution of and rationale for the change request. The resolution may be expressed in terms of one or more of the following: schedule, scope, resources, and space. The resolution description should also include a reference to the milestones impacted.